# Action Plan                                          for Liberalization of the Power Market OF THE REPUBLIC OF ARMENIA

| N | Activity | Description | Timetable | Responsible Body |
| --- | --- | --- | --- | --- |
| 1 | Amendments to the RoA Energy, Licensing, and State Duty Laws | 1.1 The MOEINR in cooperation with PSRC, develops amendments to the RoA Energy Law, including, but not limited to, the development of following amendments: Specification of MOEINR and PSRC functions Provisions to promote gradual liberalization of the WREM, including capacity market, Month-Ahead Market (MAM), Day-Ahead Market (DAM), and balancing market as well as ancillary services Unbundling of distribution and supply functions defining individual licenses and regulatory framework for each Regulating export and import activities that do not require licensing Specification and expanding of System Operator and Market Operator authorities Setting the regulatory framework for traders Provisions for nondiscriminatory access to grid and infrastructure for third parties, including new connections | May 2017 | MOEINR, PSRC |
|  |  | 1.2 The MOEINR in cooperation with PSRC, develops amendments to the RoA Licensing and State Duty Law proposing revisions to the types of licensing activity and their respective state duty amounts. | May 2017 | MOEINR, PSRC |
|  |  | 1.3 The MOEINR in cooperation with PSRC, develops and submits to the National Assembly the new Energy Law taking into consideration international best practices as well as features revealed during implementation of the new Electricity Market Model (EMM) and new Electricity Trade Mechanisms (ETM)s. | July 2020 | MOEINR, PSRC |
| 2 | Establishment of electricity Market Operator | 2.1 The PSRC, in cooperation with the MOEINR, makes amendments to the license of the Settlement Center CJSC (hereinafter Market Operator) granting it Market Operator status and new charter to organize trade in the WREM, including, but not limited to, the following: Establishment and development of the WREM Registration of WREM participants Registration and processing of WREM participants’ offers/bids for electricity purchase and sale Metering and invoicing of purchased and sold electricity on the WREM Organization of trade with neighboring WREMs | May 2017 | MOEINR, PSRC, Market Operator |
|  |  | 2.2 The PSRC, in cooperation with the MOEINR, considers revised costs of services provided by the Market Operator and any additional funds to cover new responsibilities and duties, including, but not limited to, the following: Personnel and administrative/maintenance costs for additional staff Funds for purchase and installation of optimal structure modeling software for development of new rules for the WREM | July 2017 | MOEINR, PSRC, Market Operator |
| 3 | Approval of the Grid Code and extending the legacy of the Electric Power System Operator (EPSO) | 3.1 The PSRC, in cooperation with the MOEINR, approves the energy sector Grid Code presented by the EPSO CJSC (hereinafter System Operator). | May 2017 | MOEINR, PSRC, System Operator |
|  |  | 3.2 The PSRC, in cooperation with the MOEINR, makes amendments to the license conditions of the System Operator by extending its charter to implement new tasks in accordance with Market Rules and Grid Code. | May 2017 | MOEINR, PSRC, System Operator |
|  |  | 3.3 The PSRC, in cooperation with the MOEINR, considers revised costs of services provided by the System Operator and any additional funds to cover new tasks in accordance with Market Rules and Grid Code. | July 2017 | MOEINR, PSRC, System Operator |
| 4 | Improvement of tariff structure | 4.1 The PSRC improves the distribution tariff structure based on the calculation results for each voltage level, excluding the gains/losses occurring from deviations between the planned and actual generated electricity amount, as well as the cost of service for collection of payments for the delivered electricity. | January 2018 | PSRC |
|  |  | 4.2 The PSRC improves the end-users tariff structure by voltage levels, including in the tariff calculation the actual amount of averaged costs required for electricity distribution to the particular voltage level consumers. | January 2019 | PSRC |
|  |  | 4.3 The PSRC improves the generation tariff structure for calculation of energy and capacity charge by using the same approach for depreciation and profit allocation. | January 2018 | PSRC |
|  |  | 4.4 The PSRC increases the interest rate and profit levels for generating and service-providing companies, thus improving their capability to obtain commercial loans. | January 2018 | PSRC |
|  |  | 4.5 The PSRC introduces capacity and electricity charges for new market participants entering the WREM and defines the charges for ancillary services. | July 2019 | PSRC |
| 5 | Transition to new EMM | 5.1 The PSRC, in cooperation with the MOEINR, approves temporary rules for the WREM gradual liberalization and makes: Decision on entities having the right to purchase and sell electricity by direct contracts beyond the WREM regulated market Decision on balancing mechanisms Decision on rules for electricity metering and invoicing Decision on temporary procedure for WREM entry and exit | September 2017 | MOEINR, PSRC |
|  |  | 5.2 The Market Operator implements the respective calculations using the optimal structure modeling software and, in cooperation with the System Operator and market participants, develops concepts on RoA EMM and ETMs providing them for the MOEINR and PSRC approval. New EMM and ETM concepts at least will: Guarantee large consumers, suppliers, traders, and importers entry to the WREM and organize export of electricity leftover at a particular time Introduce the mechanism for distribution of responsibilities for WREM participants Ensure full transition to the electricity hourly trading principle Provide capacity market, MAM, DAM, and balancing market as well as ancillary services Ensure the right of power plants to sell certain amounts of supplied electricity by prices exceeding the regulated tariffs | February 2018 | MOEINR, PSRC, Market Operator, System Operator |
|  |  | 5.3 The PSRC, in cooperation with the MOEINR and taking into consideration the proposals provided by the Market Operator, approves EMM and ETM concepts ensuring the implementation of obligatory requirement presented in 6.2. | July 2018 | MOEINR, PSRC, Market Operator |
|  |  | 5.4 The Market Operator launches the software selected for introduction of EMM and ETM and initiates its implementation without financial liabilities to market participants. | January 2019 | MOEINR, PSRC, Market Operator, System Operator |
|  |  | 5.5 The PSRC, in cooperation with the MOEINR and taking into consideration the proposals provided by Market Operator in compliance with EMM and ETM concepts, approves the WREM new rules and implements transition to liberalized market model with financial liabilities. | July 2019 | MOEINR, PSRC, Market Operator, System Operator |
| 6 | Unbundling of distribution and supply functions | 6.1 The PSRC introduces a new financial reporting system for the financial unbundling of distribution and supply. | September 2017 | PSRC, Distribution System Operator (DSO) |
|  |  | 6.2 PSRC approves: Distribution Grid Code Electricity trade rules on retail market Electricity distribution new contract template Electricity supply new contract template | July 2019 | PSRC, DSO |
| 7 | Elaboration of new long-term development plan | 7.1 The System Operator, in cooperation with the MOEINR, PSRC, and other state entities and interested parties including market participants, develop RoA Energy sector new long-term development plan for the next 10-year period. | July 2021 | MOEINR, PSRC, System Operator, Market Operator |

Acronyms

DAM	Day-Ahead Market

DSO	Distribution System Operator

EMM	Electricity Market Model

EPSO	Electric Power System Operator

ETM	Electricity Trade Mechanism

MAM	Month-Ahead Market

MOEINR	Ministry of Energy Infrastructures and Natural Resources

PSRC	Public Services Regulatory Commission

RoA	Republic of Armenia

WREM	Wholesale and Retail Electricity Market

U.S. Agency for International Development

1300 Pennsylvania Avenue, NW

Washington, DC 20523

Tel:  (202) 712-0000

Fax:  (202) 216-3524

www.usaid.gov